## Summary T17 (hidden)
Summary T17
Revision Date: | #REF!
Scheme Tracker
List of Contents
0.1 |  | Cover
0.2 |  | Engineering Check List
0.3 |  | Interested Parties
0.4 |  | Statutory Undertaker
0.5 |  | Sectional Agreement
0.6 |  | Third Party Fee
0.7 |  | Quotes
0.8 |  | Drawing Register
0.9 |  | Decisions Assumptions
1 |  | Technical Audit
1.1 |  | Early Warning Notification
1.2 |  | Contacts
1.3 |  | Invoice Analysis Sheet
1.4 |  | Auto Invoice
1.5 |  | Invoice 1
1.6 |  | Request Information
1.7 |  | Planning

## Consulting (hidden)
DRAWING REGISTER AND ISSUE SHEET |  |  |  |  | • Infrastructure Design |  |  |  | DRAWING REGISTER AND ISSUE SHEET |  |  |  |  | • Infrastructure Design
[5 empty] | • Structural Engineering | [8 empty] | • Structural Engineering
Client |  |  |  |  | • Planning Services |  |  |  | Client |  |  |  |  | • Planning Services
Project |  |  |  |  | • Professional Advice |  |  |  | Project |  |  |  |  | • Professional Advice
[5 empty] | • Geotechnical & | [8 empty] | • Geotechnical &
[5 empty] | Environmental | [8 empty] | Environmental
[5 empty] | • Surveying | [8 empty] | • Surveying
Project ref |  | Sheet no | P01 |  | JPP Consulting Ltd |  | T: 01604 781811 |  | Project ref |  | Sheet no | P01 |  | JPP Consulting Ltd |  | T: 01604 781811
[5 empty] | E: northampton@jppuk.net |  | W: www.jppuk.net | [6 empty] | E: northampton@jppuk.net |  | W: www.jppuk.net
Drawing No |  |  | Day | [5 empty] | Drawing No |  |  | Day
| Drawing Title |  | Month | [6 empty] | Drawing Title |  | Month
|  |  | Year | [8 empty] | Year
|  |  |  | ü | [8 empty] | ü
DISTRIBUTION |  |  |  | NUMBER OF COPIES ISSUED |  |  |  |  | DISTRIBUTION |  |  |  | NUMBER OF COPIES ISSUED
COMPANY |  | CONTACT |  | (E - issued by email) |  |  |  |  | COMPANY |  | CONTACT |  | (E - issued by email)
|  | Issued by | [8 empty] | Issued by
|  | Reason for Issue | [8 empty] | Reason for Issue
A = for cost check |  | B = for comment / approval |  |  |  | C = As requested |  | D = for tender | A = for cost check |  | B = for comment / approval |  |  |  | C = As requested |  | D = for tender
E = for information |  | F = for construction |  |  |  | R = for building regs submission |  |  | E = for information |  | F = for construction |  |  |  | R = for building regs submission
DRAWING REGISTER AND ISSUE SHEET |  |  |  |  | • Infrastructure Design |  |  |  | DRAWING REGISTER AND ISSUE SHEET |  |  |  |  | • Infrastructure Design
[5 empty] | • Structural Engineering | [8 empty] | • Structural Engineering
Client |  |  |  |  | • Planning Services |  |  |  | Client |  |  |  |  | • Planning Services
Project |  |  |  |  | • Professional Advice |  |  |  | Project |  |  |  |  | • Professional Advice
[5 empty] | • Geotechnical & | [8 empty] | • Geotechnical &
[5 empty] | Environmental | [8 empty] | Environmental
[5 empty] | • Surveying | [8 empty] | • Surveying
Project ref |  | Sheet no | P01 |  | JPP Consulting Ltd |  | T: 01604 781811 |  | Project ref |  | Sheet no | P01 |  | JPP Consulting Ltd |  | T: 01604 781811
[5 empty] | E: northampton@jppuk.net |  | W: www.jppuk.net | [6 empty] | E: northampton@jppuk.net |  | W: www.jppuk.net
Drawing No |  |  | Day | [5 empty] | Drawing No |  |  | Day
| Drawing Title |  | Month | [6 empty] | Drawing Title |  | Month
|  |  | Year | [8 empty] | Year
|  |  |  | ü | [8 empty] | ü
DISTRIBUTION |  |  |  | NUMBER OF COPIES ISSUED |  |  |  |  | DISTRIBUTION |  |  |  | NUMBER OF COPIES ISSUED
COMPANY |  | CONTACT |  | (E - issued by email) |  |  |  |  | COMPANY |  | CONTACT |  | (E - issued by email)
|  | Issued by | [8 empty] | Issued by
|  | Reason for Issue | [8 empty] | Reason for Issue
A = for cost check |  | B = for comment / approval |  |  |  | C = As requested |  | D = for tender | A = for cost check |  | B = for comment / approval |  |  |  | C = As requested |  | D = for tender
E = for information |  | F = for construction |  |  |  | R = for building regs submission |  |  | E = for information |  | F = for construction |  |  |  | R = for building regs submission

## Surveying (hidden)
DRAWING REGISTER AND ISSUE SHEET |  |  |  |  | • Infrastructure Design
• Structural Engineering
Client |  |  |  |  | • Planning Services
Project |  |  |  |  | • Professional Advice
• Geotechnical &
Environmental
• Surveying
Project ref |  | Sheet no | P01 |  | JPP Surveying Ltd |  | T: 01604 781811
[5 empty] | E: northampton@jppuk.net |  | W: www.jppuk.net
Drawing No |  |  | Day
| Drawing Title |  | Month
Year
ü
DISTRIBUTION |  |  |  | NUMBER OF COPIES ISSUED
COMPANY |  | CONTACT |  | (E - issued by email)
Issued by
Reason for Issue
A = for cost check |  | B = for comment / approval |  |  |  | C = As requested |  | D = for tender
E = for information |  | F = for construction |  |  |  | R = for building regs submission

## Geo & Enviro (hidden)
DRAWING REGISTER AND ISSUE SHEET |  |  |  |  | • Infrastructure Design
• Structural Engineering
Client |  |  |  |  | • Planning Services
Project |  |  |  |  | • Professional Advice
• Geotechnical &
Environmental
• Surveying
JPP Geotechnical &
Project ref |  | Sheet no | P01 |  | Environmental Ltd |  | T: 01604 781811
[5 empty] | E: northampton@jppuk.net |  | W: www.jppuk.net
Drawing No |  |  | Day
| Drawing Title |  | Month
Year
ü
DISTRIBUTION |  |  |  | NUMBER OF COPIES ISSUED
COMPANY |  | CONTACT |  | (E - issued by email)
Issued by
Reason for Issue
A = for cost check |  | B = for comment / approval |  |  |  | C = As requested |  | D = for tender
E = for information |  | F = for construction |  |  |  | R = for building regs submission

## Contacts page
Site Name Line 1
Inser Site Name Line 2
Insert Client Name Line 3
Insert Job Scheme number
Revision date: | 2020-03-09
Document Control
Prepared by | Ceris Wisdish
Reviewed by | Toby Heath
Authorised by | Phil Brown
JPP Design Team
Position |  | Name | Contact | Mobile
Director |  | Phil Brown | phil.brown@jppuk.net | PB: 07786 032162
Team Leader |  | Toby Heath | toby.heath@jppuk.net | TH: 07393 019651
Project Engineer |  | Warren Allsopp | warren.allsopp@jppuk.net | N/A
Project Engineer
Technician
Senior Design Co-ordinator |  | Ceris Wisdish | ceris.wisdish@jppuk.net | N/A
Design Co-ordinator |  | Beth Harrison | beth.harrison@jppuk.net | N/A
Commercial Manager
Project information
Key Project activities
Job status |  | Enquiry
Principal Designer |  | To be confirmed

## Main Cover Sheet
Site Name
To fill
Client Name
To fill
JPP Job Number
To fill
Project Tracker
Revision Date: 08/01/2019
Registered office
Northampton
4 Ironstone Way | Brixworth
Northampton
NN6 9UD
T: 01604 781811
Manchester
3rd Floor | 82 King Street
Manchester
M2 4WQ
T: 0161 682 2927
Milton Keynes
25 Linford Forum | Rockingham Drive
Linford Wood | Milton Keynes
MK14 6LY
T: 01908 889433
Poole
Suite 8 | Branksome Park House
Branksome Business Park
Bourne Valley Road | Poole | BH12 1ED
T: 01202 540888

## T38 CID - Client Inst Doc
Client Instruction Document
Company: | JPP Consulting Limited
4 Ironstone Way
Brixworth
Northampton
NN6 9UD
01604 781811
JPP Contact: | Ceris Wisdish, Senior Design Coordinator |  |  | Designcoordinatoradmin@jppuk.net
Job Scheme: | Site Name Line 1 |  | JPP Scheme Ref: | Insert Job Scheme number
Site Address:
Supporting Document:
JPP Fees & Task
JPP Term & Conditions
Copy client Instruction by email
Instructing Client Details please complete and return within 5 working days
Invoicing Client Details (If different to above) please complete and return within 5 working days
Section Agreements to collate information in readiness (as applicable)
Please add any other parties involved
Quotation Ref: |  |  | Agreed fee: | £
Start Date: |  |  | Project Duration:
This instruction document is signed and agreed on behalf
Client:
Signatory:
Print Name:
Position:
Date:
Instructing Client Details
Instructing client name:
Company address:
Registered address:
(if different from above)
Business Description (i.e. Architect, House Builder, Developer, etc.)
Company registered no:
VAT registration no:
Telephone no:
Website address:
Primary representative name:
Email address:
Telephone no:
Secondary representative name:
Email address:
Telephone no:
Clients project ref / PO number:
Principal Designer Name:
Principal Designer contact:
Comments:
Invoicing Client Details
Invoicing client name:
Company address:
Registered address:
(if different from above)
Business Description (i.e. Architect, House Builder, Developer, etc.)
Company registered no:
VAT registration no:
Telephone no:
Website address:
Accounts contact name:
Accounts telephone no:
Email address for invoicing:
Email address for statements:
Payment Terms (number of days)
Is a purchase order required: (please show format of PO for clarification) |  | YES / NO PO FORMAT **************
Purchase Order contact:
Purchase Order Authorisation Signatory contact:
Variation Order Request contact:
Variation Order Request Authorisation Signatory contact:
Comments:
JPP Internal Use only: Credit Report Date |  | CW01ENQ ( ) | CW02LIV ( ) | CW03REP ( )
Comments:
Section Agreements
Land owner name:
Land owner address:
Contractor Details
Contractor name:
Contractor address:
Additional Resource
Planning permission reference:
Planning authority:
To be provided by the Developer
Estimated cost of total development |  | £
works: |  | (This is required to assist Section Agreement application fees)
Abortive letter of undertaking: |  | See attached template letter which needs adding on to your own letterhead, signing, dating and returning with this form to enable Section Agreement applications to be submitted.
Solicitor Name:
Solicitor Address:
Registered address:
(if different from above)
Practice telephone no:
Bondsman Contact Name:
Bondsman Address:
Bondsman telephone no:
Please provide evidence of the following, where applicable
Proof of ownership of the land
Proof of an intention to enter into a Section 104 agreement and any easements (if appropriate)
Estimated cost of works: including utility company costs
Letter/Email to confirm the covering of reasonable legal costs
Details of any commuted sums - reason for them and agreed costs
Details of any easements
Construction and Design Management
Contractor Insurance Details
Proof of Operative NWR
Proposed Commencement Date of Works
Per Section Application
Risk assessment: |  | For all works to be carried out
Method statement: |  | For all works to be carried out
Location Plan Showing application |  | JPP to provide
General Layout Plan |  | JPP to provide
Comments:

## Cover Admin (hidden)
Adam Kemp | adam.kemp@jppuk.net
Aidan Marshall | aidan.marshall@jppuk.net | BA: 07769 901654
Andy Webb | andy.webb@jppuk.net | JH: 07979 863316
Becky Smith | becky.smith@jppuk.net
Beth Harrison | beth.harrison@jppuk.net | MA: 07810 806070
Ben Arnsby | ben.arnsby@jppuk.net | MF: 07979 863318
Ceris Wisdish | ceris.wisdish@jppuk.net | MT: 07825 909607
Chris | chris. @jppuk.net | NS: 07979 863315
Connor Gilbert | connor.gilbert@jppuk.net | PB: 07786 032162
Danny Barber | danny.barber@jppuk.net
Daniel Lee | daniel.lee@jppuk.net | PW: 07979 863317
David Biddulph | david.biddulph@jppuk.net | SF: 07793 863032
Deanne Kunzmann | deanne.kunzmann@jppuk.net
Deaon Tyson | deon.tyson@jppik.net | TH: 07393 019651
Emma Brown | emma.brown@jppuk.net
Gina Loizou | gina.loizou@jppuk.net | WA: 07392 080895
Jake Hayworth | jacob.hayworth@jppuk.net
Jimmy Houghton | jimmy.houghton@jppuk.net
Jon Hartley | jon.hartley@jppuk.net
Luke Clarke | luke.clarke@jppuk.net
Luke Slack | luke.slack@jppuk.net
Malcolm Baldwin | malcolm.baldwin@jppuk.net
Marc Atherton | marc.atherton@jppuk.net
Mark French | mark.french@jppuk.net
Mark Turbutt | mark.turbutt@jppuk.net
Martin Andrews | martin.andrews@jppuk.net
Matt Harrison | matt.harrison@jppuk.net
Matthew Ellisgood | matthew.ellisgood@jppuk.net
Michael Liddiard | michael.liddiard@jppuk.net
Michelle Jacquest | michelle.jacquest@jppuk.net
Nick Stairs | nick.stairs@jppuk.net
Tade Oduyale | olutade.oduyale@jppuk.net
Tom Odriscoll | tom.odriscoll@jppuk.net
Paul Wills | paul.wills@jppuk.net
Peter Knight | peter.night@jppuk.net
Phil Brown | phil.brown@jppuk.net
Rhiannon Flitcroft | rhiannon.flitcroft@jppuk.net
Richard Brighty | richard.brighty@jppuk.net
Richard Hayward | richard.hayward@jppuk.net
Sean Flannigan | sean.flannigan@jppuk.net
Simon Felton | simon.felton@jppuk.net
Spencer Furk | spencer.furk@jppuk.net
Teddy Cadby | teddy.cadby@jppuk.net
Toby Heath | toby.heath@jppuk.net
Tom Leatherland | tom.leatherland@jppuk.net
Warren Allsopp | warren.allsopp@jppuk.net
JobStatus.
Enquiry
Live Project

## Tech admin (hidden)
Title: PStatusList.
Stage 1
Stage 2
Stage 3
Other, please specify?
Title: StatusList.
Awaiting Information
Closed
Not Required
To Follow
Title: ApproveList1. | Address: |  |  |  |  | Title: ContactList. | Email: | Mob: | Tel:
Northampton Highways | Riverside House | Riverside Way | Northampton | Northamptonshire | NN1 5NX | Mark Preston | mpreston@kierwsp.co.uk | 07584253676
Bedford Group of IDBs
Leicestershire County Council | County Hall | Glenfield | Leicester | Leicestershire | LE3 8RJ | Kalel Broady | Kalel.Broady@leics.gov.uk |  | 01163050680
United Utilities
Severn Trent Water Limited
Thames Water Limited
Derbyshire County Council
Warwickshire County Council | Planning & Development Group | Transport & Economy | Communities |  |  | Dan Cresswell | danielcresswell@warwickshire.gov.uk | 01926 412622
Worcestershire County Council | [5 empty] | Steve Hutchings | Hutchings, Steven Gareth <SHutchings@worcestershire.gov.uk>
Kierwsp
Internal Email Address for Date Reminders
toby.heath@jppuk.net
Tom.Leatherland@jppuk.net
Gina.Loizou@jppuk.net
Sean.Flannigan@jppuk.net
Che-Yung.Man@jppuk.net
Ceris.Wisdish@jppuk.net
Warren.Allsopp@jppuk.net
Daniel.Lee@jppuk.net
Rhiannon.Flitcroft@jppuk.net
Aidan.Marshall@jppuk.net
luke.clarke@jppuk.net
jacob.heyworth@jppuk.net
Reference List
S23
S38
S104
S106
S184
S278

## Drawing Register- Version B (hidden)
#REF! |  |  |  |  | Site Name
#REF! |  |  |  |  | to fill
#REF! |  |  |  |  | to fill
#REF! |  |  |  |  | to fill
Revision date: | #REF! |  |  |  | Revision date: | 2017-09-07
Document title |  | Doc Rev No | Doc Type | Revision and Date Received | Document title |  | Doc Rev No | Doc Type | Revision and Date Received
|  |  | CAD or PDF | 07.09.2017 |  |  |  | CAD or PDF | 07.09.2017
DISTRIBUTION |  |  |  |  | DISTRIBUTION
COMPANY |  | CONTACT |  | (E indicates by e mail) (P indicates by Post) (D indicates Disk) (U indicates USB) | COMPANY |  | CONTACT |  | (E indicates by e mail) (P indicates by Post) (D indicates Disk) (U indicates USB)
|  | Issued By |  |  |  |  | Issued By
Reason for Issue |  |  |  |  | Reason for Issue
|  |  | CAD or PDF | 07.09.2017 |  |  |  |  | 07.09.2017
ccc
DISTRIBUTION
COMPANY |  | CONTACT |  | (E indicates by e mail) (P indicates by Post) (D indicates Disk) (U indicates USB) |  |  |  |  | (E indicates by e mail) (P indicates by Post) (D indicates Disk) (U indicates USB)
Issued By
Reason for Issue

## T17 - EDA - Eng Design Info
Site Name Line 1
Inser Site Name Line 2
Insert Client Name Line 3
Insert Job Scheme number
Revision Date |  |  | 2020-01-23
ON SITE ENGINEERING DESIGN INFORMATION CHECKLIST
Ref Key: C = Client, A = Architect, CC = Contractor, LA = Local Authority, JPP = JPP
Category |  | Item | Yes/No | Who Provides? | Further Action | Owner | Comments
Site Layout |  | Do we have the developer design standards? | No |  | Yes
|  | Do we have the developer preferred material suppliers? | No | C | Yes
|  | Site layout in CAD | Yes | A | No
|  | Does the layout use working house type drawings? | Yes | A | No
|  | Do we have the working house type drawings? | No | A | Yes
|  | Is the road layout confirmed as fixed? | N/A | A | No
|  | Are car parking areas confirmed as fixed? | Not known | A | No
|  | Are patios confirmed as fixed? | No | A | No
|  | Are paths confirmed as fixed? | No | A | No
|  | Are fences confirmed as fixed? | No | A | No
|  | Are sheds confirmed as fixed? | No | A | No
|  | Are rotary driers confirmed as fixed? | No | A | No
|  | Are water butts confirmed as fixed? | No | A | No
|  | Are compost bins confirmed as fixed? | No | A | No
|  | Are the bin stores confirmed as fixed? | No | A | No
|  | Are cycle stores confirmed as fixed? | No | A | No
|  | Do we have confirmed surface materials? | No | C/A | Yes
|  | Are the POS areas fixed? | Not known | C/A | No
|  | Do we have adoptable street lighting design? | No | C/A | Yes
|  | Conveyancing plans - Do we have the standards? | No | A | Yes
General |  | Do we have a 2D Topographical survey? | No | C | Yes
|  | Do we have a 3D Topographical survey? | No | C | Yes
|  | Has the site boundary been established and agreed? | Not known | C/A | Yes
|  | Do we have Highway extents/ boundaries? | No | C | Yes
|  | Do we have a Ground investigation report? | No | C | Yes
|  | Does the SI have all the information we need? | No | C | Yes
|  | Do we have the Planning conditions? | No | C | Yes |  | Planning Reference required, along with consent due date if known
|  | Do we have existing service records? | No | C | Yes |  | Statutory Undertaker Enquiry third party fees apply (Virgin Media & BT Openreach)
|  | Do we have existing service surveys? | No | C | Yes
Highway Design |  | Has the layout been engineering checked? | No | JPP
|  | Has swept path analysis been done? | No | JPP
|  | Are the correct vehicles being used in swept path analysis? | N/A | JPP
|  | Has the principle of permeable paving been agreed with LHA? | No | C | Yes
|  | Do we have proposed services | No | C | Yes
|  | Have we provided service corridors? (permeable paving) | N/A
|  | Do we have duct crossing plans? | No | C | Yes
|  | Do we have S278 tie in details? | N/A
|  | Do we have back of footway levels (if doing P&Es only) | N/A
|  | Do we have the S38 phasing plans? | N/A
Drainage | Planning | Is there a FRA? | Not known | C | Yes
|  | Do we agree with the FRA? | Not known | C | Yes
|  | Are there planning conditions relating to the drainage? | N/A | C | Yes
|  | Do we have the planning conditions? | N/A | C | Yes
|  | SFA 6th? | Not known | C | Yes
|  | SFA 7th? | Not known | C | Yes
|  | Do SUDS need to be provided? | Not known | JPP
| Existing | Are there existing sewers/ drains on site? | N/A
|  | Have the existing drains been accurately located? | N/A
|  | Does the existing drainage need to be diverted? | N/A
|  | Has ownership of existing drains been confirmed? | N/A
|  | Consultation with water company/ owner | N/A
| Foul | Is there a foul water outfall available? | Yes | C | Yes
|  | Is there a predevelopment enquiry with the water company? | Not known | C | Yes
|  | Is there any off site modelling works required? | N/A | C
|  | Is there any off site upgrades required? | N/A | C
|  | Is there a pumping station? | Yes | C | Yes
|  | Is there a pumping station compound layout? | Yes | C | Yes
|  | Is there a preferred rising main route? | Yes | C | Yes
|  | Is approval to go over third party land required? | Yes | C | Yes
Drainage | Storm | Do soakaways work? | Not known | C | Yes
|  | Are soakaways viable? | Not known | C | Yes
|  | Are the soakaway test results available and correct? | Not known | C | Yes
|  | Is the outfall to a riparian water course? | Not known | C | Yes
|  | Is a landowner consent required? | Not known | C | Yes
|  | Is a LLFA consent required? | Not known | C | Yes
|  | Is the outfall to Main river? | N/A
|  | Is EA consent required | N/A
|  | Is the outfall to a sewer? | N/A
|  | Is there a predevelopment enquiry with the water company? | N/A
|  | Is there adequate survey information to the outfall? | N/A
|  | Will the storm need an AIP? | N/A
|  | Will the storm need a consent to culvert? | N/A
| Agreements | S104 required? | Yes | JPP
|  | S106 required? | Yes | JPP
|  | S185 required? | No
|  | Do we have the phasing plans? | Not known
Rights of Way |  | Are there any PROW on or near to the site? | N/A | C | Yes
|  | Do we have the definitive maps? | N/A | C | Yes
|  | Has the definitive line been plotted on the Topo? | N/A | C | Yes
|  | Has the definitive line been confirmed with the ROW officer? | N/A | C | Yes
|  | Is a diversion required? | N/A | C | Yes
Party Wall |  | Are there any existing structures that are within 6m of the site? | Yes | C | Yes |  | South East of site have houses/garages within 6m.
|  | Do any boundaries offer right of support? | N/A | C | No
|  | Is any new construction within 6m of an existing boundary/ structure? | Yes | C | No |  | Yes there are proposed houses/garages within 6m of the site boundary.
|  | Has a Party Wall Surveyor been consulted? | No | C | Yes
Landscaping | Existing | Do we have a tree survey? | Yes | C | No
|  | Do we have tree root protection zones established? | Yes | C | No
|  | Do we have trees identified 30m beyond the site boundary? | Not known | C | No
|  | Have the aerial photos been checked for trees on and off site? | No | C | No
|  | Have historic maps been checked? | No | C | No
|  | Has the client been notified of deficient tree survey information? | No | C | No
| Prop | Do we have the proposed landscaping drawings? | No | C | No
Ecology |  | Are there any ecological constraints? | Not known | C | No
Noise |  | Is there a noise survey? | Yes | C | No
|  | Is there a noise bund? | Yes | C | No
|  | Have we checked the noise bund will fit? | Yes | C | No
Additional Information |  | Description | Date | Rev | Engineer | Checked | Comments
|  | Information that JPP provide: | Owner:
|  | S38 designs | Who is Principal designer
S104 designs
Private drainage design
Private level design
Flow control structures
Extents of retaining
Drained area plan

## Sectional Admin 2 (hidden)
SectionList. | SectionDescription. | Notes.
Statutory Undertaker | Utility Plans - Gas, Electric, Broadband, etc.
Asset Plans - Water groups
Highway Boundary's | Highway Extents
Public Rights Of Way | You have the right to access some land for walking or certain other leisure activities. You can: use public roads and pavements or public rights of way, for example footpaths or bridleways.
Other | Other
Building Control
Manufacturer / supplier specifications
Environment Agency
Planning Applications
Section 23, Land Drainage Consent Act – 1991 | S23 Control of flow of watercourses. Prohibition on obstructions etc. in watercourses
Section 38, Highways Act 1980 - Adoption of highways on private owned land. | S38 A local highway authority can enter into a legal agreement with a developer to adopt a highway provided the highway has been constructed to a specified standard and to the satisfaction of the local highway authority.
Section S278, Highways Act 1980. Works within an existing public highway in which there are agreements as to the execution of works. | The Section 278 agreement is a legally binding document between the Local Highway Authority and the developer to ensure that the work to be carried out on the highway is completed to the standards and satisfaction of the Local Highway Authority.
Street Lighting Design
Section 104, Water Industry Act 1991. | S104 Agreements to adopt sewer, drain or sewage disposal works, at future date.
Section 106, Water Industry Act 1991. | S106 Right to communicate with public sewers. Any person interested in land in the area of a local planning authority may, by agreement or otherwise, enter into an obligation.
Pre Development | Find out if Waterboard's existing wastewater network can support your proposed development. If it can't, they will need to carry out a fuller study called a drainage impact assessment.
CCTV
Road Safety Audit | Pre Dev - A Road Safety Audit (RSA) is defined as the formal safety performance examination of an existing or future road or intersection. So they identify road safety problems and to suggest measures to eliminate any concerns.
Section 50, New Roads and Street Works Act 1991 | S50 Street works licences.
Section 98, Water Industry Act 1991 | S98 Requisition a new public sewer or public lateral drain
Section 184, Highways Act 1980 | S184 Vehicle crossings over footways and verges.
Section 185, Water Industry Act 1991 | S185 Sewer diversions
Build Over Agreement, Water Industry Act 1991 | Build Over - For building work you plan to have carried out over or near a public sewer owned by the Waterboard.
Public Footpath Diversion Order | Application for public footpath diversion order if connected to a planning decision
Vehicle Access | Vehicle Access -Dropped Kerb / Cross over. Is when crossing across a public footpath or verge for your vehicle to get to your property from the road.
Section 247, Town and Country Planning Act 1990 | S247 Highway stopping-up or diversion orders.
Stopping Up Orders | Stopping Up - Go to press, council send letter = time sensitive (8 weeks)
Temporary Road Closures | Temporary Road Closures - council groups
Trade Effluent | Trade Effluent - Petrol stations
Status.
On Hold
Approval Received
Consent Received
Drawings
Cancelled
Closed
Chase
Client Chq's in
Client Chq's fwd.
Internal Chase
Instruction to Proceed
JPP Chq's fwd.
Outstanding
Quotes
Outstanding.
Planning permission
Reserved Matters
Land Title
Ecology Report
CCTV
GI Survey
Estimates Cost of Works
Risk Assessment
Method Statement
Technical Details
Internal Notes
Designer Response
Technical Comments
Topo Survey
ItemsReceived.
Yes
No
To follow

## T17 SA - Sectional Tracker
Site Name Line 1
Inser Site Name Line 2 | [6 empty] | SECTIONAL TRACKER
Insert Client Name Line 3
Insert Job Scheme number
Revision Date: | 2020-03-09
Sectional Agreement List |  | Section Description | Required Yes/No | Status | Outstanding | Items Received | Date | Time | Contact | Comments | Response Time (Days)
|  |  | Yes |  | GI Survey | To follow
Other
Other
Manufacturer / supplier specifications
Other
Other |  |  | To be confirmed | [7 empty] | Days to Consent | #VALUE!
Other |  |  | To be confirmed | [7 empty] | Days to Consent | 0
Other |  |  | To be confirmed | [7 empty] | Days to Consent | 0
Other |  |  | To be confirmed | [7 empty] | Days to Consent | 0

## T17 TA - Technical Audit
Site Name Line 1
Inser Site Name Line 2 |  |  | TECHNICAL AUDIT
Insert Client Name Line 3
Insert Job Scheme number
Revision Date: |  | 2020-03-09
Approving Authority |  | Warwickshire County Council
Address
Audit Status |  | Stage 3 | Issue
Reference |  | S104
Contact |  |  | Email
Internal Note: Do not pdf these two columns for client
Date | Item | Comment |  | Designer Response | Date Responded | Internal Email
Approving Authority |  | Warwickshire County Council
Address
Audit Status |  | Stage 3 | Issue
Reference |  | S104
Contact |  |  | Email
Internal Note: Do not pdf these two columns for client
Date | Item | Comment |  | Designer Response | Date Responded | Internal Email
Approving Authority |  | Kierwsp
Address
Audit Status |  | Stage 1 | Issue
Reference |  | S184
Contact |  |  | Email
Internal Note: Do not pdf these two columns for client
Date | Item | Comment |  | Designer Response | Date Responded | Internal Email

## T11-DR Civils Drawing Regis
CIVILS DRAWING REGISTER AND ISSUE SHEET
Client | Insert Client Name Line 3
Project | Site Name Line 1
Project ref | Insert Job Scheme number | Sheet no | P01 |  |  |  |  | JPP Consulting Ltd |  | T: 01604 781811
[8 empty] | E: mail@jppuk.net |  | W: www.jppuk.net
Drawing No |  |  | Day | Current Issue | 1 | 2 | 3
| Drawing Title |  | Month |  | 02 | 02 | 02
|  |  | Year |  | 10 | 10 | 10
C1 | Drawing Title 1 |  | pdf | ü | T1 | T2 | T3
C2 | Drawing Title 2 |  | pdf |  | T1 |  | T2
C3 | Drawing Title 3 |  | pdf |  |  |  | T1
DISTRIBUTION |  |  |  | NUMBER OF COPIES ISSUED
COMPANY |  | CONTACT |  | (E - issued by email)
Issued by
Reason for Issue
A = for cost check |  | B = for comment / approval | [6 empty] | C = As requested |  | D = for tender
E = for information |  | F = for construction | [6 empty] | R = for building regs submission
CIVILS DRAWING REGISTER AND ISSUE SHEET
Client | 0
Project | 0
Project ref | 0 | Sheet no | P02 |  |  |  |  | JPP Consulting Ltd |  | T: 01604 781811
[8 empty] | E: mail@jppuk.net |  | W: www.jppuk.net
Drawing No |  |  | Day | Current Issue
| Drawing Title |  | Month
Year
DISTRIBUTION |  |  |  | NUMBER OF COPIES ISSUED
COMPANY |  | CONTACT |  | (E - issued by email)
Issued by
Reason for Issue
A = for cost check |  | B = for comment / approval | [6 empty] | C = As requested |  | D = for tender
E = for information |  | F = for construction | [6 empty] | R = for building regs submission

## T11-DR Struct Drawing Regis
STRUCTURES DRAWING REGISTER AND ISSUE SHEET
Client | Insert Client Name Line 3
Project | Site Name Line 1
Project ref | Insert Job Scheme number | Sheet no | P01 |  |  |  |  | JPP Consulting Ltd |  | T: 01604 781811
[8 empty] | E: mail@jppuk.net |  | W: www.jppuk.net
Drawing No |  |  | Day | Current Issue | 1 | 2 | 3
| Drawing Title |  | Month |  | 02 | 02 | 02
|  |  | Year |  | 20 | 20 | 20
S1 | Structural Drawing Title 1 |  | pdf | ü | T1 | T2 | T3
S2 | Structural Drawing Title 2 |  | pdf |  | T1 |  | T2
S3 | Structural Drawing Title 3 |  | pdf |  |  |  | T1
DISTRIBUTION |  |  |  | NUMBER OF COPIES ISSUED
COMPANY |  | CONTACT |  | (E - issued by email)
Issued by
Reason for Issue
A = for cost check |  | B = for comment / approval | [6 empty] | C = As requested |  | D = for tender
E = for information |  | F = for construction | [6 empty] | R = for building regs submission

## T27 GIR - Gen Info Register
GENERAL INFORMATION REGISTER
Client | Insert Client Name Line 3
Project | Site Name Line 1
Project ref | Insert Job Scheme number | Sheet no | P01 |  | Northampton Office |  | T: 01604 781811
[5 empty] | E: mail@jppuk.net |  | W: www.jppuk.net
Ref No |  |  | Day
| Document Title |  | Month
Year
ü
DISTRIBUTION |  |  |  | NUMBER OF COPIES ISSUED
COMPANY |  | CONTACT |  | (E - issued by email)
Issued by
Reason for Issue
A = for cost check |  | B = for comment / approval |  |  |  | C = As requested |  | D = for tender
E = for information |  | F = for construction |  |  |  | R = for building regs submission

## EWN Tracker
Early Warning Notice (EWN) Tracker
Project Title | [5 empty] | Latest Update:
Nr: | [5 empty] | Prepared By: | JPP
[5 empty] | Key: |  | DUE IN 1 WEEK/LATE
DUE IN 28 DAYS
EWN Number | Description | Reason for EWN | Submitted to for action | Date required | EWN Status |  | Comments/implications | Closed out Y/N | Cost effect Y/N
[5 empty] | Date Requested | Date Fully received
001 | [6 empty] | Potential Change | N | Y
002 | [6 empty] | Potential Change | N | Y
003 | [6 empty] | Potential Change | N | Y
004 | [6 empty] | Potential Change | N | Y
005 | [6 empty] | Potential Change | N | Y
006 | [6 empty] | Potential Change | N | Y
007 | [6 empty] | Potential Change | N | Y
008 | [6 empty] | Potential Change | N | Y
009 | [6 empty] | Potential Change | N | Y
010 | [6 empty] | Potential Change | N | Y
011 | [6 empty] | Potential Change | N | Y
012 | [6 empty] | Potential Change | N | Y
013 | [6 empty] | Potential Change | N | Y
014 | [6 empty] | Potential Change | N | Y
015 | [6 empty] | Potential Change | N | Y
016 | [6 empty] | Potential Change | N | Y
017 | [6 empty] | Potential Change | N | Y
018 | [6 empty] | Potential Change | N | Y
019 | [6 empty] | Potential Change | N | Y
020 | [6 empty] | Potential Change | N | Y
021 | [6 empty] | Potential Change | N | Y
022 | [6 empty] | Potential Change | N | Y
023 | [6 empty] | Potential Change | N | Y
024 | [6 empty] | Potential Change | N | Y
025 | [6 empty] | Potential Change | N | Y
026 | [6 empty] | Potential Change | N | Y
027 | [6 empty] | Potential Change | N | Y
028 | [6 empty] | Potential Change | N | Y

## RFI VOR Tracker
Request for Information (RFI) Tracker
Project Title | [5 empty] | Latest Update:
Nr: | [5 empty] | Prepared By: | JPP
TRACKER TO BE ISSUED AND REVIEWED AT MONTHLY CLIENT SITE MEETING |  |  |  |  | Key: |  | DUE IN 1 WEEK/LATE
DUE IN 28 DAYS
RFI Number | Description | Reason for RFI | Submitted to for action | Date required | RFI Status |  | Comments/implications | Closed out Y/N | Cost effect Y/N
[5 empty] | Date Requested | Date Fully received
001
002
003
004
005
006
007
008
009
010
011
012
013
014
015
016
017
018
019
020
021
022
023
024
025
Variation Order Request (VRO) Tracker
Project Title | [5 empty] | Latest Update:
Nr: | [5 empty] | Prepared By: | JPP
TRACKER TO BE ISSUED AND REVIEWED AT MONTHLY CLIENT SITE MEETING |  |  |  |  | Key: |  | DUE IN 1 WEEK/LATE
DUE IN 28 DAYS
VOR Number | Description | Reason for VOR | Submitted to for action | Date required | VOR Status |  | Comments/implications | Closed out Y/N | Cost effect Y/N
[5 empty] | Date Requested | Date Fully received
001
002
003
004
005
006
007
008
009
010
011
012
013
014
015
016
017
018
019
020
021
022
023
024
025

## F11-VOR
VARIATION ORDER REQUEST (VOR)
VOR Ref No.
Project |  | Site Name Line 1
Project Ref |  | Insert Job Scheme number |  |  |  | Date
Client |  |  |  | Contact
Contact No |  |  |  | Email address
We hereby agree to the specified changes and charges listed below:
| Will delays occur due to these works being carried out |  |  |  | YES / NO
If yes, state impact on programme if any
| Additional charge for above changes is |  | £
JPP Contact details
| Raised by |  |  | Contact details
CLIENT ACCEPTANCE
| Print Name |  |  | Date
| Position |  |  | Additional PO nr (if required)

## EWN
Early Warning Notification
Revision Date:
Project Title: |  |  |  |  | Job Number:
Issued to: |  |  |  |  | Early Warning Notification number:
Early Warning Title: |  |  |  |  | Issue Date:
This event could (Yes/No as appropriate)
Increase the total of the price |  |  | Delay Completion |  |  | Change the accepted programme | Delay Meeting a Key Date
Yes |  |  | Yes |  |  | Yes | Potentially
The matter notified is as follows:
Relevant Drawings and other Documents:
Anticipated additional time and cost, if known at this stage:
Not known
The programme for completion will be, if known at this stage:
Not known
Response from Engie:
Distribution
| Y | Employer |  | Quantity Surveyor
|  | Consultant |  | Site copy
Engineer

## T43-RFI Request for Information
Request for Information (RFI)
Job Scheme Ref Number: | JPP-RFI-00 |  | Date:
Job Scheme Name: | Site Name Line 1 |  | Job Scheme Number: |  |  |  | Insert Job Scheme number
Contract Number:
To Company: |  |  | Contact Name:
Contact Phone: |  |  | Contact Email:
Request Title: | Any service routes within ground beneath the MSCP |  |  |  |  | Cost Effect Y/N |  |  | £
Type of Request: | Clarify Y/N | Conflict Y/N |  |  |  | Suggest Y/N |  |  | Other Y/N
Documents affected by RFI: | Specification: |  |  | Drawing: |  |  |  | Detail:
Request issued by: |  |  | Position:
Requestor Phone: |  |  | Requestor Email:
Information Requested:
Response |  |  |  |  | Required Date:
Responded By:
Date:
Accepted:
Design Updated:
Client approved:

## T17 SU - Statutory Undertaker
Site Name Line 1 |  |  |  |  | STATUTORY UNDERTAKER ENQUIRY
Inser Site Name Line 2
Insert Client Name Line 3
Insert Job Scheme number
Revision Date: | 2020-03-09
Invoicing Client:
Site Address:
Grid Reference: E: N:
Scheme Description:
Planning Permission Ref:
Land Owner Details:
Statutory Undertaker | Contact Email Address | Contact Name | Address |  |  | Email Date | Response Date | Plant Affected? | Diversion Cost | Comments | Enquiry Cost | Invoice to Client | Response Time (Days)
National Grid/Cadent | plantprotection@cadentgas.com | 0800 688 588 |  | www.beforeyoudig.nationalgrid.com | [5 empty] | Ref: 11237H Our Ref: XX_XX_ 3SWX_506588 |  |  | 0
Western Power | [12 empty] | 0
Anglian Water | [9 empty] | Asset Plans third party fee applies and form to fill | 0 | 0 | 0
Severn Trent Water | [9 empty] | Asset Plans third party fee applies and form to fill | 0 | 0 | 0
Sussex Water | [12 empty] | 0
Thames Water | [9 empty] | Asset Plan third party fee applies | 0 | 0 | 0
Wessex Water | [12 empty] | 0
Virgin Media | [9 empty] | Asset Plan third party fee applies | 0 | 0 | 0
Openreach (BT) | [9 empty] | Asset Plan third party fee applies (online) | 0 | 0 | 0
UK Power Networks | [12 empty] | 0
Electricity North West | [12 empty] | 0
Wales & West Utilities Ltd | [12 empty] | 0
[10 empty] | Cumulative Enquiry Cost | 0 | 0
Cumulative Cost charged to client

## T17 TPF - Third Party Fee
Site Name Line 1 |  |  |  | THIRD PARTY FEE TRACKER
Inser Site Name Line 2
Insert Client Name Line 3
Insert Job Scheme number
Revision Date: |  | 2020-03-09
Item | Description |  |  |  | Sectional Agreement | Payable to: | £ | Received YES /NO | Internal Note: This section is not to be pdf to client
[10 empty] | Net VAT | Inc VAT | JPP 20%
| Anglian Water Wastewater |  |  |  | Asset Plan | JPP to add as a disbursement | 0 |  | Digdat /Anglian Water |  | 38.4 | 46.08
| Severn Trent Water, Water and Sewer |  |  |  | Asset Plan | JPP to add as a disbursement | 0 |  | Severn Trent Water | 30 | 36 | 43.2
| Virgin Media |  |  |  | Asset Plan | JPP to add as a disbursement | 0 |  | Virgin Media | 43 | 51.6 | 61.92
| BT Openreach |  |  |  | Asset Plan | JPP to add as a disbursement | 0 |  | BT Openreach | 52.92 | 63.5 | 76.2
| Thames Water |  |  |  | Asset Plan | JPP to add as a disbursement | 0 |  | Thames Water Asset Plan | 46.34 | 57.92 | 69.5
| UK Power Networks |  |  |  | Asset Plan | JPP to add as a disbursement | 0 |  | Uk Power Networks |  | 50 | 60
[9 empty] | Highway Boundary Extents | 70 |  | 84
[9 empty] | Highway Public Right of Way | 70 |  | 84
435.62
Please arrange for Bacs payment to be made to:
JPP Consulting Ltd/TA as the John Parkhouse Partnership
Sort Code: 56:00:60
Account No: 35102667
| Scheme Ref: |  | #REF! | #REF!

## T17 SQ - Supplier Quotes
Site Name Line 1
Inser Site Name Line 2 |  | SUPPLIER QUOTES
Insert Client Name Line 3
Insert Job Scheme number
Revision Date: | 2020-03-09
Ref: | Supplier |  | Date Available | Description | Cost | Approved Yes/No
1 |  |  |  |  | 0
2 |  |  |  |  | 0
3 |  |  |  |  | 0
4 |  |  |  |  | 0
5 |  |  |  |  | 0
6 |  |  |  |  | 0

## T27 BQ - Budget Quote
Site Name Line 1 |  |  |  |  | Budget Quote - New Development Utility Connections
Inser Site Name Line 2
Insert Client Name Line 3
Insert Job Scheme number
Revision Date: | 2020-03-09
Invoicing Client:
Site Address:
Grid Reference: E: N:
Scheme Description:
Planning Permission Ref:
Land Owner Details:
Statutory Undertaker | Contact Email Address | Contact Name | Address |  |  | Email Date | Response Date | Plant Affected? | Diversion Cost | Comments | Enquiry Cost | Invoice to Client | Response Time (Days)
National Grid/Cadent | plantprotection@cadentgas.com | 0800 688 588 |  | www.beforeyoudig.nationalgrid.com | [5 empty] | Online application 10 working days for asset plan issue//www.beforeyoudig.nationalgrid.com |  |  | 0
Western Power | [12 empty] | 0
Anglian Water | [9 empty] | Asset Plans third party fee applies and form to fill | 0 | 0 | 0
Severn Trent Water | [9 empty] | Asset Plans third party fee applies and form to fill | 0 | 0 | 0
Sussex Water | [12 empty] | 0
Thames Water | [9 empty] | Asset Plan third party fee applies | 0 | 0 | 0
Wessex Water | [12 empty] | 0
Virgin Media | [9 empty] | Asset Plan third party fee applies | 0 | 0 | 0
Openreach (BT) | [9 empty] | Asset Plan third party fee applies (online) | 0 | 0 | 0
UK Power Networks | [12 empty] | 0
Electricity North West | [12 empty] | 0
Wales & West Utilities Ltd | [12 empty] | 0
[10 empty] | Cumulative Enquiry Cost | 0 | 0
Cumulative Cost charged to client
frontdeskrequests@wwutilities.co.uk; shaun.smith@wwutilities.co.uk; cnewton@westernpower.co.uk; developerservices@thameswater.co.uk; newsites.general@openreach.co.uk; plantprotection@nationalgrid.com; plantenquiries@instalcom.co.uk; asset.team@cityfibre.com; plantenquiries@catelecomuk.com; plantenquiries@energetics-uk.com; nrswa@cofely-gdfsuez.com; gcchighways@amey.co.uk; https://pe.gtc-uk.co.uk/PlantEnqMembership; interoute.enquiries@plancast.co.uk:; kpn.plantenquiries@instalcom.co.uk; mbnl.plant.enquiries@turntown.com; nrswa@sky.uk; SOTA.plantenquiries@instalcom.co.uk; assetrecords@utilityassets.co.uk; osp-team@uk.verizonbusiness.com; osm.enquiries@atkinsglobal.com; https://plant.interoute.com/plant-enquiries

## T17 DA - Decisions Assumptions
Site Name Line 1
Inser Site Name Line 2 |  |  |  | Design decisions and assumptions
Insert Client Name Line 3
Insert Job Scheme number
Revision Date: |  | 2020-03-09 | [9 empty] | Internal use only
Item Ref | Date Raised | Discipline | Location | Design Decision or Assumption | Description of Decision or Assumption | Originator Company | Originator Name | Justification | Further Action or Evidence | Stakeholder Affected | Affected Stakeholder Sign Off or Closed Out | Review Date | Prepared by | Approved by
| 2017-01-01 | Structural | where on site, e.g., road 2 ch 30 | Decision |  | JPP |  |  |  | TW
|  | Infrastructure |  | Assumption | [5 empty] | Highways
|  | planning | [7 empty] | AW
Contractor

## T17 EWN - Early Warning Not (hidden)
Site Name Line 1 |  |  | Early Warning Notification
Inser Site Name Line 2
Insert Client Name Line 3
Insert Job Scheme number
Revision Date: | 2020-03-09
Employer Address |  |  |  |  | Job Number
Consultant Address |  |  |  |  | Early Warning Notification number
Project Address |  |  |  |  | Issue Date
This event could (Yes/No as appropriate)
Increase the total of the price | Delay Completion | Change the accepted programme |  | Delay Meeting a Key Date |  | Impair the Performance of the works in use | Affect the work of the Employer, an Employer's contractor or another consultant
In accordance with the conditions of the contract the matter notified is as follows:
Detail of instruction
Relevant Drawings and other Documents:
Response required by
JPP response
The programme for completion will be
JPP Consulting Grade |  |  |  | Hourly Rate |  |  | Hours Required
Directors |  |  |  | 0
Associate Directors
Associate Directors
Leading Engineer
Senior Engineer/Leading/Technician
Main grade Engineer/Senior Technician
Assistant Engineer/Main grade Technician
Graduate Engineer
Assistant Technician
Distribution
| Employer |  | Quantity Surveyor |  |  | Signed:
| Consultant |  | Site copy
| Engineer |  |  |  |  | For JPP Consulting

## Section Fees (hidden)
Regular Section Agreement Price Sheet (taken from Services spreadsheet)
Authority | Section | Fee | Contacts
Leicesteshire County Council | S38 | #REF!
Leicesteshire County Council | S278 | #REF!
Northamptonshire County Council | S38 | #REF!
Northamptonshire County Council | S278 | #REF!
Milton Keynes Council | S38 | #REF! | Jonjo McBride
Milton Keynes Council | S278 | #REF!
Oxfordshire County Council | S38 | #REF!
Oxfordshire County Council | S278 | #REF!

## Drawing Register (hidden)
#REF!
#REF! |  |  |  | DRAWING REGISTER & ISSUE SHEET
#REF!
#REF!
Revision date: | #REF!
Revision and Date received
Document title |  | Document Reference |  | Document type | 01.02.2017
No of Copies Issued ð
Engineering Layout |  | 100 |  | pdf
Long Sections |  | 101 |  | pdf
Manhole Schedules |  | 102 |  | pdf
Adoptable Drainage Construction Details |  | 103 |  | pdf
Adoptable Highway Construction Details |  | 104 |  | pdf
Private Drainage and External Levels |  | 105 |  | pdf
Section 104 Layout |  | 106 |  | pdf
Section 38 Layout |  | 107 |  | pdf
Surface Finishes Layout |  | 108 |  | pdf
Flood Routing Layout |  | 109 |  | pdf
Swept Path Analysis |  | 110 |  | pdf
Road Setting Out |  | 111 |  | pdf
House Setting Out |  | 112 |  | pdf
Plot Boundary Setting Out |  | 113 |  | pdf
Designers Risk Assessment Plan |  | 114 |  | pdf
SW Manhole Schedules |  | 150 |  | pdf
FW Manhole Schedules |  | 151 |  | pdf
Section 278
Site Location Plan |  | 200 |  | pdf
General Arrangement Plan |  | 201 |  | pdf
Site Clearance Plan |  | 202 |  | pdf
Materials Layout |  | 203 |  | pdf
Kerb Construction Layout |  | 204 |  | pdf
Signing and Lining Layout |  | 205 |  | pdf
Highway Construction Details |  | 206 |  | pdf
Drainage Layout |  | 207 |  | pdf
Finished Contour Plan |  | 208 |  | pdf
Long Sections |  | 209 |  | pdf
Existing Services |  | 210 |  | pdf
Designers Risk Assessment Plan |  | 211 |  | pdf
Section 38
S38 Layout |  | 300 |  | pdf
Longitudinal Sections (1 of 4) |  | 305 |  | pdf
Longitudinal Sections (2 of 4) |  | 306 |  | pdf
Longitudinal Sections (3 of 4) |  | 307 | 308 | pdf
Longitudinal Sections (4 of 4) |  | 308 | 310 | pdf
S38 Kerbing Plan |  | 310 | 311 | pdf
S38 Kerbing Plan |  | 311 | 312 | pdf
S38 Kerbing Plan |  | 312 | 315 | pdf
S38 Materials Layout |  | 315 |  | pdf
S38 Gully Spacing Plan |  | 316 |  | pdf
S38 Site Clearance Plan |  | 317 |  | pdf
S38 Signage Plan |  | 318 |  | pdf
S38 Carriageway Construction Details |  | 320 |  | pdf
S38 Carriageway Construction Details |  | 321 |  | pdf
S38 Drainage Construction Details – Sheet 1 |  | 322 |  | pdf
S38 Vehicle Tracking (Sheet 1 of 12) |  | 330 |  | pdf
S38 Vehicle Tracking (sheet 2 of 12) |  | 331 |  | pdf
S38 Vehicle Tracking (sheet 3 of 12) |  | 332 |  | pdf
S38 Vehicle Tracking (sheet 4 of 12) |  | 333 |  | pdf
S38 Vehicle Tracking (sheet 5 of 12) |  | 334 |  | pdf
S38 Vehicle Tracking (sheet 6 of 12) |  | 335 |  | pdf
S38 Vehicle Tracking (sheet 7 of 12) |  | 336 |  | pdf
S38 Vehicle Tracking (sheet 8 of 12) |  | 337 |  | pdf
S38 Vehicle Tracking (sheet 9 of 12) |  | 338 |  | pdf
S38 Vehicle Tracking (sheet 10 of 12) |  | 339 |  | pdf
S38 Vehicle Tracking (sheet 11 of 12) |  | 340 |  | pdf
S38 Vehicle Tracking (sheet 12 of 12) |  | 341 | 341 | pdf
S38 Sections Through Junction Visibility Splays |  | 350 |  | pdf
Section 104
Section 104 Layout |  | 400 |  | pdf
S104 Drainage Construction Details |  | 406 |  | pdf
S104 North Headwall Construction Details |  | 407 |  | pdf
S104 South Headwall Construction Details |  | 408 |  | pdf
S104 Section Through Outfalls |  | 409 |  | pdf
Proposed Gas Main Crossings |  | E500 |  | pdf
Site Location Plan |  | S01 |  | pdf
Section 106
Section 104 Layout |  | 400 |  | pdf
S104 Drainage Construction Details |  | 406 |  | pdf
S104 North Headwall Construction Details |  | 407 |  | pdf
S104 South Headwall Construction Details |  | 408 |  | pdf
S104 Section Through Outfalls |  | 409 |  | pdf
Proposed Gas Main Crossings |  | E500 |  | pdf
Flood Routing Layout |  | 109 |  | pdf
Site Location Plan |  | S01 |  | pdf
DISTRIBUTION
COMPANY |  | CONTACT |  | (E indicates by e mail) (P indicates by Post) (D indicates Disk) (U indicates USB)
Issued By
Reason for Issue
B= Comment Approval |  | A= For Cost Check |  | C = As Requested | D = For Tender | E = For Information |  | F = Construction | R = B.Regs submission
Hand Delivery By: |  |  |  |  | Received Date: Recipient Name:
please insert your name in capitals letters |  |  |  |  | please insert your name in capitals letters

## Invoice Analysis Sheet
Site Name Line 1
Inser Site Name Line 2
Insert Client Name Line 3
Insert Job Scheme number
Revision Date: | 2020-03-09
Invoice Summary
Task | Agreed fee | % | Amount invoiced to date | cum tot
Statutory Undertaker Enquiry | 100 | 50% | 50 | 50
Highway Boundary Record | #REF! | 0% | #REF! | #REF!
Public Rights of Way | #REF! | 0% | #REF! | #REF!
Pre Development Enquiry | #REF! | 0% | #REF! | #REF!
| #REF! | 0% | #REF! | #REF!
| #REF! | 0% | #REF! | #REF!
| #REF! | 0% | #REF! | #REF!
| #REF! | 0% | #REF! | #REF!
| #REF! | 0% | #REF! | #REF!
| #REF! | 0% | #REF! | #REF!
| #REF! | 0% | #REF! | #REF!
| #REF! |  | 0 | #REF!
| #REF! |  | 0 | #REF!
| #REF! |  | 0 | #REF!
| #REF! |  | 0 | #REF!
| #REF! |  | 0 | #REF!
| #REF! |  | 0 | #REF!
| #REF! |  | 0 | #REF!
| #REF! |  | 0 | #REF!
| #REF! |  | 0 | #REF!
Invoice | Amount | Sub Total
1/ | 0 | 0
2/ | 0 | 0
3/ | 0 | 0
4/ | 0 | 0
5/ | 0 | 0
6/ | 0 | 0
7/ | 0 | 0 | outstanding | 0 | 0
8/ | 0 | 0 | outstanding | 0 | 0
9/ | 0 | 0 | outstanding | 0 | 0
0
Amount paid | 0
Credit amount | #REF! | +VAT

## Invoice Analysis Sheet 2
Invoice Dates |  |  | 2019-05-16 | [7 empty] | Projected 2
SERVICE |  | TOTAL FEE | Interim Invoice 1 | Interim Invoice 2 | Interim Invoice 3 | Interim Invoice 4 | Interim Invoice 5 | Interim Invoice 6 | Interim Invoice 7 | Interim Invoice 8 | Interim Invoice
0
|  | Invoice total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Application | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Balance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TP Bridgewater Invoice Analysis v PACS Purchase Order |  |  |  | 11.05 | 11.13 | 11.14 | 11.2 | 11.21 | 11.25
|  |  |  | Structural Engineer | Topographical Survey and Report | Ground floor slab core testing survey & report | Utility surveys & consultants | Ground investigations | Drainage surveys & consultants | Totals
Invoice No. | Uploaded to PACs | Invoice Date | Amount (-VAT) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ball
|  |  | 0 | 0 | [5 empty] | 0 | 0
|  |  | 0 | [6 empty] | 0 | 0
|  |  | 0 |  |  | 0 |  |  |  | 0 | 0
|  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0
|  |  | 0 | 0 | [5 empty] | 0 | 0
|  |  | 0 |  | 0 |  |  |  |  | 0 | 0
|  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  | 0 |  |  |  |  | 0 |  | 0 | 0
|  |  | 0 |  |  |  |  | 0 |  | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
|  | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Balance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Sheet1 (hidden)
Gedling Appointment Confirmation |  |  |  | • Infrastructure Design
• Structural Engineering
• Planning Services
Client | Keepmoat |  |  | • Professional Advice
Project | Arnold Lane, Gedling |  |  | • Geotechnical &
Project Ref | 9443H |  |  | Environmental
• Surveying
JPP Consulting Ltd T: 01604 781811
W: www.jppuk.net
Phase | Invoice No. | Appointment Date | Fee and Task Schedule | Task
Phase 1A1 / 1A
| 1-33612 | 30th January 2018 @ 17:23 agreed by Alan Staley | Fee agreed £1224.00 - 24hr technician @ £36/hr and 5hr Senior Project Engineer @ £72/Hr | Providing pile setting out drawings for Phase 1A
| 1-33612 | 30th January 2018 @ 17:23 agreed by Alan Staley | £2,772 + VAT | Providing plans and sections to suit approved retaining wall heights and incorporating level changes and options
| 1-33612 | 30th January 2018 @ 17:23 agreed by Alan Staley | £1,080 + VAT | Amending turning head and private drives adjacent to plots 104-109 and 115-116, providing a levels and drainage plan
| 1-33612 | 30th January 2018 @ 17:23 agreed by Alan Staley | £1,224 + VAT | Providing pile setting out drawings for phase 1A
| 1-33612 | 30th January 2018 @ 17:23 agreed by Alan Staley | £2,760 + VAT | Providing drainage review of entire site to determine if larger pond could be reduced
| 2-33713 | 31st January 2018 @ 17:05 agreed by Alan Staley | £3750 + VAT | To reviewing drainage strategy and FFC's for re-plan area.
| 2-33713 | 31st January 2018 @ 17:05 agreed by Alan Staley | £2150 + VAT | To providing private levels and drainage designs for a re-plan area
| 7-33966 / CR-12-34335 / 13-34336 | 20th April 2018 @ 16:39 agreed by Ben Douglas | Section 38 - £1000.00 - Then credited (Keepmoat paid direct) Section 106 - £192.82 | Sectional Agreement payments (S38 and 106)
| 9-34044 | As per agreed fee and task schedule | £2136 + VAT | To providing levels review of phase 1A and providing drawings
| 11-34269 | 12th June 2018 @ 08:15 as agreed between Warren and Ben Douglas | £950 + VAT | To providing FFL's for the 30 ILKE plots
| 14-34423 | 2nd May 2018 @15:40 agreed by Ben Douglas | £495 + VAT | To providing plot and boundary setting out for Phase 1A
| 15-34480 | 22nd August 2018 @11:03 agreed by Ben Douglas | £2050 + VAT as per Fee and Task Schedule | To undertaking the Pile Design and setting out for plots 21-27 of Phase 1
| 21-34779 | 26th October 2018 @ 15:31 agreed by Ben Douglas | £2401.5 + VAT | To undertaking remedial work to Plot 176
| 23-34901 | 30th November 2018 @ 09:01 agreed by Ben Douglas | £324 + VAT - 4.5hrs Senior Engineer Rate | Providing on-going advice and enginering support for items wthin Phase 1A1 on hourly rates
| 25-35536 & 26-35683 | 23rd April 2019 @ 12:57 agreed by Victoria Oxford | £1,600 + VAT | To undertaking additional works for Phase 1A - Section 278 General Arrangement Plan
| 25-35536 & 29-35896 | 23rd April 2019 @ 12:57 agreed by Victoria Oxford | £1,450 + VAT | To undertaking additional works for Phase 1A - Plot 48-63 Apartment Block Level Design
| 25-35536 & 29-35896 | 23rd April 2019 @ 12:57 agreed by Victoria Oxford | £1,850 + VAT | To undertaking additional works for Phase 1A - Phase 1 Road 4 Adoption RRRAP assessment
| 26-35683 | 23rd April 2019 @ 16:36 agreed by Rob Hannan | £525 + VAT | To undertaking additional works for Phase 1A - For undertaking balcony structural calculations
Phase 1A2/ 1B
| 3-33717 & 4-33826 | 2nd February 2018 @ 07:16 agreed by Sean Barratt | £500 per house type £1500 per apartment block All three blocks = £7,250 + VAT | To providing superstructure designs for 3no. Apartment blocks
| 3-33717 & 4-33826 | 2nd February 2018 @ 07:16 agreed by Sean Barratt | Cost for the superstructure design will £1500 + VAT for each block = £4500 + VAT | To providing piled foundation designs for 3no. Apartment blocks
| 5-33874 | 20th February 2018 @ 09:39 agreed by Alan Stanley | £5250 + VAT. Based on £550 per house type variation (including garages) and £100 per plot. | To carry out pile design to include pile layout, pile loads, ground beam design and details and setting out
| 5-33874 | 19th March 2018 agreed by Sean Barratt | £1350 + VAT | To providing piled foundation design for bin stores.
| 6-33921 & 24-35134 | As per agreed fee and task schedule 20th February 2018 | £28,000 + VAT | To providing Civil Engineer design
| 8-33996 & 10-34205 | 20th February 2018 @ 09:39 agreed by Alan Staley | £15,918 + VAT - breakdown provided in Fee & Task Schedule | To providing Structural Engineer design
| 14-34423 | 2nd May 2018 @15:40 agreed by Ben Douglas | £495 + VAT | To providing plot and boundary setting out for Phase 1B
| 19-34706 & 28-35685 | As agreed between Tom Leatherland and Ben Douglas | £4,350 +VAT | On site Private Drainage and External Levels for llke
| 30-35897 | 29th August 2019 @ 14:11 agreed by Victoria Oxford | £2950 + VAT | For undertaking foundation recommendations for Ilke plots 329-358 Phase 1C
Phase 1B/ 1C
| 16-34593 / CR-17-34704 / 20-34707 / 27-35684 / | 12th July 2018 @ 12:18 agreed by Ben Douglas | £28,000 + VAT - Fee & Task Schedule Rev A | Phase 1C - on site infrastructure works
| 16-34593 / CR-17-34704 / | 12th July 2018 @ 12:18 agreed by Ben Douglas | £4,350 + VAT - Fee & Task Schedule Rev A | On site Private Drainage and External Levels for Ilke Plots
| 16-34593 / CR-17-34704 / 18-34705 | 21st September 2019 @15:19 agreed by Ben Douglas | £735 + VAT - Fee & Task Schedule | For undertaking private drainage amendments to MEC drainage layout
| 31-35898 | 4th June 2019 @ 09:59 agreed by Victoria Oxford | £15,080 + VAT - 104 Plots @ £145 per plot | Private Drainage & External Levels
| 31-35898 | 4th June 2019 @ 09:59 agreed by Victoria Oxford | £5,720 + VAT - 104 Plots @ £55 per plot | Foundation Recommendations
Phase 2
| 22-34780 | 26th October 2018 @ 15:31 agreed by Ben Douglas | 41000 | For undertaking works for Phase 2
| 32-35899 | 29th July 2019 @ 14:11 agreed by Victoria Oxford | £1,117.50 + VAT | For undertaking preliminary Road Layouts/Level strategy for Phase 2 based on the latest requirements from Keepmoat

## Foundation Schedule (hidden)
Beanfield School | [5 empty] | Foundation Schedule
Corby
Northamptonshire
U8633PH
Revision date: |  |  | 2017-08-18
Plot Number | Finish Floor Level (m) |  |  | Foundation Lowest Level (m) |  | Foundation Highest Level (m) |  | Foundation Lowest Width (mm) | Foundation Highest Width (mm) | Comments
1 | FFL | 127 | 700 | 124 | 300 | 124 | 800 | 750 | 900 | This schedule is a summary only and shall not be solely used for tender, setting out and construction. For full foundation design and details please refer to the drawings U8633/PH 'F series'
2 | FFL | 128 | 000 | 128 | 300 | 128 | 800 | 750 | 900
3 | FFL | 128 | 300 | 125 | 300 | 125 | 300 | 750 | 900
4 | FFL | 128 | 600 | 125 | 300 | 126 | 300 | 450 | 900
5 | FFL | 128 | 000 | 126 | 650 | 126 | 650 | 450 | 450
6 | FFL | 128 | 450 | 126 | 650 | 126 | 650 | 450 | 600
7 | FFL | 128 | 700 | 126 | 300 | 126 | 900 | 450 | 750
8 | FFL | 128 | 700 | 126 | 000 | 126 | 600 | 450 | 750
9 | FFL | 128 | 900 | 126 | 000 | 126 | 300 | 450 | 750
10 | FFL | 128 | 900 | 126 | 000 | 126 | 600 | 450 | 750
11 | FFL | 129 | 100 | 126 | 100 | 126 | 400 | 450 | 750
12 | FFL | 129 | 100 | 125 | 800 | 126 | 400 | 450 | 750
13 | FFL | 129 | 100 | 125 | 800 | 126 | 700 | 600 | 750
14 | FFL | 129 | 100 | 126 | 100 | 127 | 000 | 450 | 750
15 | FFL | 129 | 000 | 126 | 600 | 126 | 900 | 450 | 600
16 | FFL | 128 | 550 | 126 | 900 | 127 | 200 | 450 | 600
17 | FFL | 128 | 100 | 126 | 100 | 126 | 400 | 450 | 450
18 | FFL | 127 | 650 | 126 | 400 | 126 | 400 | 450 | 600
19 | FFL | 128 | 450 | 125 | 800 | 126 | 400 | 450 | 450
20 | FFL | 128 | 750 | 125 | 200 | 125 | 800 | 750 | 750
21 | FFL | 128 | 600 | 126 | 600 | 126 | 600 | 450 | 750
22 | FFL | 128 | 300 | 126 | 600 | 126 | 600 | 450 | 750
23 | FFL | 128 | 500 | 126 | 800 | 126 | 800 | 450 | 600
24 | FFL | 128 | 400 | 126 | 800 | 126 | 800 | 450 | 600
25 | FFL | 128 | 400 | 126 | 800 | 126 | 800 | 450 | 600
26 | FFL | 128 | 200 | 126 | 850 | 126 | 850 | 450 | 750
27 | FFL | 128.2 | 200 | 126 | 850 | 126 | 850 | 450 | 750
28 | FFL | 128 | 300 | 126 | 900 | 126 | 900 | 450 | 600
29 | FFL | 128 | 300 | 126 | 900 | 126 | 900 | 450 | 600
30 | FFL | 128 | 550 | 127 | 100 | 127 | 100 | 450 | 600
31 | FFL | 129 | 000 | 127 | 100 | 127 | 100 | 450 | 600
32 | FFL | 129 | 600 | 127 | 200 | 127 | 200 | 600 | 600
33 | FFL | 129 | 900 | 127 | 200 | 127 | 200 | 600 | 600
34 | FFL | 130 | 000 | 127 | 600 | 127 | 600 | 450 | 750
35 | FFL | 130 | 100 | 127 | 600 | 127 | 600 | 450 | 750
36 | FFL | 129 | 850 | 127 | 800 | 127 | 800 | 450 | 600
37 | FFL | 129 | 850 | 127 | 800 | 127 | 800 | 450 | 600
38 | FFL | 128 | 350 | 126 | 500 | 126 | 500 | 450 | 750
39 | FFL | 128 | 650 | 126 | 500 | 126 | 500 | 450 | 750
40 | FFL | 129 | 100 | 126 | 800 | 127 | 100 | 600 | 750
41 | FFL | 129 | 550 | 127 | 100 | 127 | 400 | 600 | 750
42 | FFL | 129 | 600 | 127 | 200 | 127 | 200 | 450 | 750
43 | FFL | 129 | 600 | 127 | 200 | 127 | 200 | 450 | 750
44 | FFL | 129 | 800 | 127 | 800 | 127 | 800 | 450 | 600
45 | FFL | 129 | 800 | 127 | 100 | 127 | 100 | 600 | 600
46 | FFL | 130 | 000 | 127 | 900 | 128 | 400 | 450 | 600
47 | FFL | 130 | 300 | 128 | 200 | 128 | 600 | 450 | 750
48 | FFL | 130 | 300 | 127 | 900 | 128 | 200 | 450 | 750
49 | FFL | 130 | 300 | 127 | 900 | 128 | 600 | 450 | 750
50 | FFL | 130 | 300 | 128 | 900 | 128 | 900 | 450 | 750
51 | FFL | 130 | 300 | 128 | 900 | 128 | 900 | 450 | 750 | This schedule is a summary only and shall not be solely used for tender, setting out and construction. For full foundation design and details please refer to the drawings U8633/PH 'F series'
52 | FFL | 130 | 300 | 128 | 900 | 128 | 900 | 450 | 750
53 | FFL | 129 | 900 | 127 | 700 | 127 | 700 | 450 | 600
54 | FFL | 129 | 900 | 127 | 700 | 127 | 700 | 450 | 600
55 | FFL | 129 | 750 | 127 | 600 | 127 | 600 | 450 | 450
56 | FFL | 129 | 750 | 127 | 600 | 127 | 600 | 450 | 450
57 | FFL | 129 | 600 | 127 | 700 | 127 | 700 | 450 | 450
58 | FFL | 129 | 600 | 127 | 700 | 127 | 700 | 450 | 450
59 | FFL | 129 | 700 | 127 | 650 | 127 | 650 | 450 | 450
60 | FFL | 129 | 700 | 127 | 650 | 127 | 650 | 450 | 450
61 | FFL | 129 | 700 | 127 | 900 | 127 | 900 | 450 | 450
62 | FFL | 129 | 700 | 127 | 900 | 127 | 900 | 450 | 450
63 | FFL | 128 | 900 | 127 | 200 | 127 | 200 | 450 | 450
64 | FFL | 128 | 900 | 127 | 200 | 127 | 200 | 450 | 450
65 | FFL | 129 | 200 | 127 | 200 | 127 | 500 | 450 | 450
66 | FFL | 129 | 200 | 127 | 200 | 127 | 500 | 450 | 450
67 | FFL | 129 | 500 | 127 | 300 | 127 | 600 | 450 | 450
68 | FFL | 129 | 500 | 127 | 600 | 127 | 600 | 450 | 450
69 | FFL | 129 | 400 | 127 | 400 | 127 | 400 | 450 | 450
70 | FFL | 129 | 400 | 127 | 400 | 127 | 400 | 450 | 450
71 | FFL | 129 | 100 | 126 | 900 | 127 | 200 | 450 | 450
72 | FFL | 129 | 100 | 126 | 900 | 127 | 200 | 450 | 450
73 | FFL | 129 | 000 | 127 | 500 | 127 | 500 | 450 | 450
74 | FFL | 129 | 000 | 127 | 500 | 27 | 500 | 450 | 450
75 | FFL | 128 | 900 | 126 | 200 | 126 | 500 | 600 | 750
76 | FFL | 128 | 900 | 125 | 300 | 125 | 900 | 600 | 750
77 | FFL | 128 | 650 | 126 | 500 | 127 | 100 | 450 | 450
78 | FFL | 128 | 650 | 126 | 800 | 127 | 100 | 450 | 450
79 | FFL | 128 | 650 | 127 | 300 | 127 | 300 | 450 | 450
80 | FFL | 128 | 650 | 127 | 300 | 127 | 300 | 450 | 450

## Approved Schedule 1 (hidden)
#REF!
#REF!
#REF! |  |  | S38 Approved Drawings Schedules
#REF!
Revision date: |  | #REF!
Client |  | BQ Farms
Drawn By |  | WRA
Checked By |  | WRA
Drawing Number | Drawing Title
300F | S38 Layout
305D | Longitudinal Sections (1 of 4)
306D | Longitudinal Sections (2 of 4)
307D | Longitudinal Sections (3 of 4)
308D | Longitudinal Sections (4 of 4)
310E | S38 Kerbing Plan
311E | S38 Kerbing Plan
312E | S38 Kerbing Plan
315E | S38 Materials Layout
316C | S38 Gully Spacing Plan
317C | S38 Site Clearance Plan
318C | S38 Signage Plan
320B | S38 Carriageway Construction Details
321B | S38 Carriageway Construction Details
322 | S38 Drainage Construction Details – Sheet 1
323 | S38 Drainage Construction Details – Sheet 3
330C | S38 Vehicle Tracking (Sheet 1 of 12)
331C | S38 Vehicle Tracking (sheet 2 of 12)
332C | S38 Vehicle Tracking (sheet 3 of 12)
333C | S38 Vehicle Tracking (sheet 4 of 12)
334C | S38 Vehicle Tracking (sheet 5 of 12)
335C | S38 Vehicle Tracking (sheet 6 of 12)
336C | S38 Vehicle Tracking (sheet 7 of 12)
337C | S38 Vehicle Tracking (sheet 8 of 12)
338C | S38 Vehicle Tracking (sheet 9 of 12)
339C | S38 Vehicle Tracking (sheet 10 of 12)
340C | S38 Vehicle Tracking (sheet 11 of 12)
341C | S38 Vehicle Tracking (sheet 12 of 12)
350 | S38 Sections Through Junction Visibility Splays
#REF!
#REF!
#REF! |  |  | S104 Approved Drawings Schedules
U8499PR
Revision date: |  | #REF!
Client |  | BQ Farms
Drawn By |  | WRA
Checked By |  | WRA
Drawing Number | Drawing Title
305D | Longitudinal Sections (1 of 4)
306D | Longitudinal Sections (2 of 4)
307D | Longitudinal Sections (3 of 4)
308D | Longitudinal Sections (4 of 4)
105B | Drained Area Plan
110C | Private Drainage Layout
150C | SW Manhole Schedules
151B | FW Manhole Schedules
400E | S104 Layout
406B | S104 Drainage Construction Details
407 | S104 North Head Wall Construction Details
408 | S104 South Head Wall Construction Details
409B | S104 Sections Through Outfalls

## Template (hidden)
#REF! |  | Document Title
#REF!
#REF!
#REF!
Revision date: | #REF!

## Approved Schedule 2 (hidden)
#REF!
#REF!
#REF! |  |  | S104 Approved Drawings Schedules
#REF!
Revision date: |  | #REF!
Client |  | BQ Farms
Drawn By |  | WRA
Checked By |  | WRA
Drawing Number | Drawing Title
305D | Longitudinal Sections (1 of 4)
306D | Longitudinal Sections (2 of 4)
307D | Longitudinal Sections (3 of 4)
308D | Longitudinal Sections (4 of 4)
105B | Drained Area Plan
110C | Private Drainage Layout
150C | SW Manhole Schedules
151B | FW Manhole Schedules
400E | S104 Layout
406B | S104 Drainage Construction Details
407 | S104 North Head Wall Construction Details
408 | S104 South Head Wall Construction Details
409B | S104 Sections Through Outfalls

## Section Agree Admin (hidden)
ValidCheck.
To be confirmed
Yes
No

## Contacts (hidden)
#REF! |  | CONTACTS
#REF!
#REF!
#REF!
Revision Date: | #REF!
Name | Organisation |  | Role | Email | Phone (landline) | Phone (mobile)

## Invoice 1 (hidden)
Site Name |  | Invoice / Statement
#REF!
#REF!
#REF!
#REF!
Revision Date: | #REF!
Invoice No. |  |  | / |  | /
Date:
| Phoenix Surfacing Ltd | [7 empty] | Dir |  |  | Eng |  |  | Client |  |  | Name |  |  | Building name |  |  | Address 1 |  |  | Address 2 |  |  | Town |  |  | County |  |  | Postcode |  |  | Scheme
[9 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
For the attention of Sam Eaton
To implementing Statutory Undertaker Enquiry
| Digdat | [5 empty] | 36.96 | 20%JPP added
| Virgin Media | [5 empty] | 51.6 | Gross
| Openreach | [5 empty] | 63.5 | Gross
| Design Coordinator charge rate per hour £51.00 total 5 hours | [5 empty] | 255 | CW Fees
| Sub total | [5 empty] | 407.06
less previous
| Total | [5 empty] | 407.06
| Plus VAT @ 20% | [5 empty] | 0
| Total | [5 empty] | 407.06
PLEASE NOTE OUR TERMS ARE STRICTLY 30 DAYS NETT
For payments by BACS our account details are:
National Westminster Bank plc, Drapery Branch, Northampton
Account no. 35102667 Sort Code 56-00-60
Ref: | 0 | 0 | / | 0 | / | 0
VAT No. 120 0308 47
Cedar Barn, White Lodge, Walgrave,
Northampton NN6 9PY
T: (01604) 781811 E: mail@jppuk.net
F: (01604) 781999 W: www.jppuk.net

## Template1 (hidden)
Site Name Line 1
Inser Site Name Line 2 |  |  |  | REQUEST FOR FURTHER INFORMATION
Insert Client Name Line 3
Insert Job Scheme number
Revision Date: |  | 2020-03-09
RFI No | From |  | Date Received | Query | Date Closed | By